## Slide 1: Project Status Report: COBWeb
Executive Summary | From the start of the project until the date of our status report, Kaizen has been developing documentation regarding the project’s plan, requirements, team member expectation, and defining the overall course of the COBWeb platform. The actual development of the platform is currently almost at the 75% stage.​
Recent Accomplishments
Development and finalization of all project support documentation (Statement of Work, Project Management Plan, Project Charter, Requirements Management Plan) Completed setting up account and adding requirements to our dashboard (Shortcut.com) Completed setting up account for WordPress as our CMS Divided and Assigned requirements to members Format of the platform Found plug-ins to accommodate the needs and wants of the platform Prototypes reviewed
Next Steps
Entering 75% of final stages of development Polishing up cosmetics (visuals and styling) of pages Adding/editing missing components to pages
Milestones |  |  | 
Milestone | Baseline | Expected | RAG
Finalization of Statement of Work, Project Management Plan, Project Charter, Requirements Management Plan | 10/6 | 10/6 | C
Adding requirements to dashboard (Shortcut.com) | 10/6 | 10/6 | C
Finalization of domain name/URL and CMS to use | 10/6 | 10/6 | C
Risks, Issues, and Dependencies
Shortcut.com accounts are required to proceed with requirements tracking. Some plug-ins require a "business" upgrade on WordPress that cost money.
Status Key: | Green: On Target | Amber: Risks to Timeline, Scope, or Budget | Red: Requires Corrective Action | Complete: Work Complete
Status Date | 11/07/2021
Project Sponsor | Robert Barker
Project Team | Kaizen
RAG Status | Green
Notes: Need a high-level dashboard for operational leaders. Must tell the whole story (single source of truth for staffing, outreach, engagement, etc.).
Focus on CM and DM first. We don’t have good contact information for members. Bi-weekly update meeting.